## Implemention Schedule
|  | Responsible | [5 empty] | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4
No | Main Activities | Customer | ACTouch Tech | Days | Responsibilty | From date | To Date | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Day 15 | Day 16 | Day 17 | Day 18 | Day 19 | Day 20 | Day 21 | Day 22 | Day 23 | Day 24 | Day 25 | Day 26 | Day 27 | Day 28 | Status | Actual Start date | Actual Completion date | Remarks
1 | Project Initiation | Identify the Project Leader and project teams | Identify the Project Leader | 1
|  | Check the contract document and see any specific agreements | 1. Scope of the modules to implements 2. Reports and Customization, if any
|  | Agree on the project scope | Define the proect scope as per contract
|  | Agree on the project timelines |  | Mile Stone
2 | Current system study | Customer to answer the Questions and fill the data | Share the system study document to Customer to fill it | 3
3 | Project Data collecton | Prepare Product Group | Share the excel format & verify the data, once its done | 1
|  | Outbound eMail configuration and message template |  | 0.5
|  | Units of Measurements, Alternate UOM, MUOM |  | 0
|  | Site / Branches, if any |  | 0
|  | Location Master, if any |  | 0
|  | Tax Master |  | 0
|  | Product Master |  | 2
Product master with Planning parameters, if any
Product master with Tally software mapping data, if any
|  | Vendor / Supplier Master |  | 0.5
|  | Customer Master |  | 0.5
|  | Bank Master |  | 0
|  | Accounts Verification and check |  | 0
|  | Accounts Category and define new, if any |  | 0
|  | Multi Currency, if any |  | 0
|  | Bill of Material (for Manufacturing) |  | 1
|  | Work centers (for Manufacturing) |  | 0.5
|  | Tools details (for Manufacturing) |  | 0.5
Quality test cases, if any
Customer and Product Price lists
Supplier and product price lists
|  | Sales person and commissions master |  | 0
|  | Approve the data |  | Mile Stone
4 | Data Migration | Upload the data | Support the process | 1
5 | Customization | Identify the Invoice formats and other print formats | Prepare the documents
|  | Approve the scope and features list | Prepare the documents
Share the delivery timelines
Complete the development
Release the product to Customer
6 | Training | Agree on the timelines, allocate the people and identify who are the "user champions" | Add the Customised components for Training | 0
|  | Allocate the people for the training. Do hands-on training sessions | ACTouch to deliver the training | 2
|  | Training completion signoff |  | Milestone
7 | User Acceptance Testing |  | Prepare the UAT environment | 0
|  | Identify the business scenarios Prepare the test cases. |  | 2
|  | Prepare the UAT plans and Approve | Allocate a person to support | 2
|  | Execute the UAT and complete the testing | Allocate a person to support | 3
|  | Check reports, Print invoices etc |  | 1
|  | Identfy the issues, if any | Fix the issues | 1
|  | UAT completion signoff |  | Mile stone
8 | Go Live Preparation | Customer to decide Cut-off date for Go Live |  | 0
Data migration and Open Balance
|  | Product Master |  | 1
Vendor / Supplier Master
Customer Master
Open Invoices - By Customer wise
Open Purchase receipts - By Supplier wise
Opening Stock with LOCATION and BATCH wise Details
Accounting entries - Trial Balance
if NO Trial balance data then opening BANK and CASH balance entries
|  | Control file setups |  | 1
User master and allocation of menu access rights
General Setting
Inventory control files
Sales Control file
Purchase Control file
| Go live | Begin the live transactions, check reports
Support the customer and address the issues, if any
| Post Go live support | Project completion sign off

## System study plans
No | Modules | Mandatory/Optional | Person Responsible | Date of delivery | Mode of data entry (Upload / manual entry)

## Users created with menu access
No | User ID | Role in Company | Major Menu access | Date of Creation
1 | abc@abcc.com | Purchase and Sales | Purchase orders. POR. Sales Orders Invocing | 2017-10-10

## Master Data preparation
No | Modules | Mandatory/Optional | Person Responsible | Date of delivery | Mode of data entry (Upload / manual entry)
1 | Product Group | Based on customer needs. But explain the business scenarios |  |  | Manual entry
2 | Define Product ID and the numbering formats. 1. Raw materials. (Bought out items) 2. Semi finished goods 3. Finished Goods 4. Consumable items | This is prepare customer to format the Product ID
3 | Check Tax Master. | Be careful with INPUT and OUTPUT Taxes |  |  | Manual entry
4 | Check Unit of Measurements. | Ensure that you have the necessary details before you begin uploading the Product Master |  |  | Manual entry
5 | Create alternate UOM | Create alternate UOM, its impact on BOM, FGR, PO, SO etc |  |  | Manual entry
6 | Multi UOM and how its impact on BOM, Sales, Purchase and FGRs, if any | Depending on Customer needs |  |  | Manual entry
7 | Create Users with email ids and their menus acces rights | Check the another sheet for detailed entries |  |  | Manual entry
8 | Location masters – Here you can attach the users and the location rights. | This menu is only for those who wants to use LOCATION features. Important: if you have subcontractors then create one LOCATION per subcontractor so that you can track the materials sent to them through Delivery Challans. |  |  | Manual entry
9 | Product master upload 1. Product ID less than 20 char * 2. Description less than 250 char * 3. Unit of measurements * 4. Do you keep stock / Inventory = Yes * 5. Product Group 6. If the QTY is entered then Unit Price is important as it gives inventory valuations. * 7. Enter Selling price 8. Check Purchase or Sales TAXES (VAT/ Excise / Non Excise) 9. Check whether product is maintained in “batches” or not 10. HSN Codes | Either you can create manually or Upload the data from menus. |  |  | Data upload from Application / Manual
10 | After product master upload is done, you can do these for those | Enter the Excise details, if EXCISE = YES, 1. Manually enable those items that are EXCISE 2. Enter the HSN Codes. |  |  | Manual entry
11 | Customer Master 1. Customer ID * 2. Customer Name * 3. GSTN Number and state 4. eMail id 5. Address |  |  |  | Data upload from Application / Manual
12 | Supplier / vendor master 1. Suppier ID * 2. Supplier Name * 3. GSTN Number and state 4. eMail id 5. Address |  |  |  | Data upload from Application / Manual
13 | Bank Master. | If more than one Bank then create the same number of GL Bank Account codes too. One Bank Master Code = One Bank GL Account Code |  |  | Manual entry
14 | Accounts Master and Accounts Category, if any | 1. Create new Assets, Sales, or expense accounts, if required 2. Accounts category helps us to plan for the BS and PL reports |  |  | Manual entry
15 | Multi Currency enablement and set the exchange rates | For Multi currency users only |  |  | Manual entry
16 | Bill of Materials: To make a finished goods (FG), what and all raw materials (RM)/components required | For Manufacturing Customers only. Important to note 1. Product ID should be matched to the Product ID that’s created. 2. Be careful with Scrap and other percentage details 3. By Product features can be enabled from the Menus. |  |  | Data upload from Application / Manual
17 | Employee Master - You can attach the Login ID to employees. | Optional |  |  | Manual entry
18 | Sales persons and their commission details | Optional |  |  | Manual entry

## Training plans
|  | Customer Name |  |  |  | Note
|  | Date of training |  |  | 1 | Add or remove the Modules list based on customer needs
|  | Trained by |  |  | 2 | Daywise scheudle is made and shared with customers
Training Location
Attendees
Modules that are trained as below
|  | Modules | Date of training | Signatures
| 1 | Purchase menu
1. Purchase Order – Inventory – Creation, Update of PO, Print and Views
a. Purchase with Receipt of Materials and Payments
b. Pay the Advance to Suppliers
2. Purchase Order – Service – Creation, Update of PO, Print and Views
3. Purchase Order – Excise – Creation, Update of PO, Print and Views
4. Purchase Order Receipt / Goods Receipts Notes (GRN) – Inventory, Service and Excise
5. POR – Inventory, Service and Excise – UPDATE and Change the Data
6. Purchase returns – Inventory, Service and Excise
7. Import Purchase Receipts – Helps to pay Customs duty and Logistics separately.
| 2 | Sales Order Menu
1. Sales Order – Inventory – Creation, Update of SO, Print and Views
a. Sales orders with delivery of Materials and Receive Payments
b. Receive the Advance to Suppliers
2. Sales Order – Service – Creation, Update of SO, Print and Views
3. Sales Order – Excise – Creation, Update of SO, Print and Views
4. Shipments – Inventory, Service and Excise
5. Shipments– Inventory, Service and Excise – UPDATE and Change the Data
6. Sales Returns – Inventory, Service and Excise
7. Print Delivery Challans
| 3 | Sales Quotations
a. SQ – Inventory – Creation, Update of SQ, Print and Views
b. SQ– Service – Creation, Update of SO, Print and Views
c. Keep the SQ versions
d. Convert SQ to SO (Inventory / Services)
| 4 | Manufacturing module – Inhouse production
a. Control File to see the features to be enabled for your needs
b. Bill of Materials
a. Fields likes Don’t show Price, User access controls and Hide RM list from showing to end users.
b. By product features
c. ABC (Activity based costing)
a. Labour
b. Machine
c. Burden costs
d. Copy BOM
c. Finished goods reporting – Receive the FG /WIP from production location
d. Issue Materials to Shop floor for the Production
e. Production Orders
a. Create production Orders from Sales Orders
b. Reports Production orders – Issue materials, Receive Finished Goods etc
c. Reports
f. Work Orders
a. Masters
i. Create Work centres
ii. Create Operation codes
iii. Create Tools
iv. Create Routing Codes
b. Work Order Creations
c. Reports
| 5 | Manufacturing module – Subcontracting
a. Subcontractor Job work
b. Subcontractor Outward DC and send materials for subcontracting work
c. Inward DC – Receive the FG and consume the RM. Track the remaining RM at vendors place
d. Convert IDC to PO / POR for payment and settlements
| 6 | Manufacturing module – Job work
a. Job worker’s Job work
b. Job worker’s Outward DC and send FG
c. Job worker’s Inward DC – Receive the RM and consume the RM.
d. Track the remaining RM at vendors place
| 7 | Accounts Receivable
AR for Inventory and Services
a. Selection of Multiple Invoices for Payments
b. Part payments / Full payments – Selection of Advance, Credit Notes
Other Income and Advance Receipts
| 8 | Accounts Payable
AP for Inventory and Services
a. Selection of Multiple Invoices for Payments
b. Part payments / Full payments – Selection of Advance, Debit Notes
Expense Payments and Advance Payments
| 9 | General Ledger
1. Journal Entries and Contra Entry
2. Debit and Credit notes
3. Balance Sheet, Profit and Loss Sheet and Trial Balance reports
4. VAT report and Pay to Government
5. Handle Interstate taxes
6. Excise Features
a. For Traders
b. Manufacturers
c. All the Excise Reports.
d. Central Excise module with reports to track FG, Sales etc.
| 10 | Multi Currency
Ability to handle multiple levels of currencies
Track the Exchange Gain or Loss amounts based on agreed price and final paid price
| 11 | Warranty menu
a. AMC Setups
b. Jobwork creation
c. Invoicing
A sample Training plan that can be shared with customers
Days |  | Contents
Day 1 | First Half | About ACTouch.com | Overall and Navigation
10 AM to 1 PM
|  | Master data | Customers, Vendors, Accounts, Taxes, Product Groups etc
|  | Admin Features | Create Users, Create Companies, Data transfer, Opening Stock entry
|  | Purchase Cycle | PO, Goods receipt notes, PO Returns
|  | Inventory Management | Issues and Receipts
| Second Half | Sales Cycle | Sales Orders, Shipment and Invoicing, Sales Returns
2 PM to 5 PM
|  | Financials | Payments and Receipts
|  | General Ledger | Journal Entry, Bank and Cash Transfer
|  | Taxes | Taxes and reports
Day 2 | First Half | 30 Min Revision | Answer Questions.
10 AM to 1 PM
|  | Manufacturing | Bill of Materials, Finished Goods Reporting, Subcontracting, Job work and its management
|  | Reports | Inventory Reports
Sales Reports
Purchase Reports
| Second Half | Hands-on sessions | Used in case there is a need to address more queries
2 PM to 5 PM

## Customer UAT Plans
|  |  | 2018-01-01 |  | 2018-01-02 |  | 2018-01-03 |  | 2018-01-04
Modules to test | Customer team | ACTouch.com team | Morning | Afernoon | Morning | Afernoon | Morning | Afernoon | Morning | Afernoon
Purchase menu
1. Purchase Order – Inventory – Creation, Update of PO, Print and Views
a. Purchase with Receipt of Materials and Payments
b. Pay the Advance to Suppliers
2. Purchase Order – Service – Creation, Update of PO, Print and Views
3. Purchase Order – Excise – Creation, Update of PO, Print and Views
4. Purchase Order Receipt / Goods Receipts Notes (GRN) – Inventory, Service and Excise
5. POR – Inventory, Service and Excise – UPDATE and Change the Data
6. Purchase returns – Inventory, Service
7. Import Purchase Receipts – Helps to pay Customs duty and Logistics separately.
Sales Order Menu
1. Sales Order – Inventory – Creation, Update of SO, Print and Views
a. Sales orders with delivery of Materials and Receive Payments
b. Receive the Advance to Suppliers
2. Sales Order – Service – Creation, Update of SO, Print and Views
3. Sales Order – Excise – Creation, Update of SO, Print and Views
4. Shipments – Inventory, Service and Excise
5. Shipments– Inventory, Service and Excise – UPDATE and Change the Data
6. Sales Returns – Inventory, Service and Excise
7. Print Delivery Challans
Sales Quotations
a. SQ – Inventory – Creation, Update of SQ, Print and Views
b. SQ– Service – Creation, Update of SO, Print and Views
c. Keep the SQ versions
d. Convert SQ to SO (Inventory / Services)
Manufacturing module – Inhouse production
a. Control File to see the features to be enabled for your needs
b. Bill of Materials
a. Fields likes Don’t show Price, User access controls and Hide RM list from showing to end users.
b. By product features
c. ABC (Activity based costing)
a. Labour
b. Machine
c. Burden costs
d. Copy BOM
c. Finished goods reporting – Receive the FG /WIP from production location
d. Issue Materials to Shop floor for the Production
e. Production Orders
a. Create production Orders from Sales Orders
b. Reports Production orders – Issue materials, Receive Finished Goods etc
c. Reports
f. Work Orders
a. Masters
i. Create Work centres
ii. Create Operation codes
iii. Create Tools
iv. Create Routing Codes
b. Work Order Creations
c. Reports
Manufacturing module – Subcontracting
a. Subcontractor Job work
b. Subcontractor Outward DC and send materials for subcontracting work
c. Inward DC – Receive the FG and consume the RM. Track the remaining RM at vendors place
d. Convert IDC to PO / POR for payment and settlements
Manufacturing module – Job work
a. Job worker’s Job work
b. Job worker’s Outward DC and send FG
c. Job worker’s Inward DC – Receive the RM and consume the RM.
d. Track the remaining RM at vendors place
Accounts Receivable
AR for Inventory and Services
a. Selection of Multiple Invoices for Payments
b. Part payments / Full payments – Selection of Advance, Credit Notes
Other Income and Advance Receipts
Accounts Payable
AP for Inventory and Services
a. Selection of Multiple Invoices for Payments
b. Part payments / Full payments – Selection of Advance, Debit Notes
Expense Payments and Advance Payments
General Ledger
1. Journal Entries and Contra Entry
2. Debit and Credit notes
3. Balance Sheet, Profit and Loss Sheet and Trial Balance reports
4. VAT report and Pay to Government
5. Handle Interstate taxes
6. Excise Features
a. For Traders
b. Manufacturers
c. All the Excise Reports.
d. Central Excise module with reports to track FG, Sales etc.

## Go live checklist
No |  | Items to check | Remarks | Approved by | Is uploaded
1 | Preparation | General settings 1. Enable Serial numbers 2. Enable the menus that’s required for the customers
2 |  | Check the testing environment to see, any specific needs been developed
3 |  | Ensure that customisation components are moved to new environments
4 |  | Ensure that customised Invoices, PO, SO etc are moved into new environment
5 |  | Check the Number of User Licenses sold to customers
6 |  | Check the contract signed and see whats been agreed to deliver to customers
1 | Master Data | Templates and terms and conditions
2 |  | eMail ID configuration for outbound emails
3 |  | Configuration of email message templates
4 |  | Product Group
5 |  | Check Tax Master.
6 |  | Check Unit of Measurements.
7 |  | Alternate UOM and how its impact on BOM, Sales, Purchase and FGRs | Depending on Customer needs
8 |  | Multi UOM and how its impact on BOM, Sales, Purchase and FGRs, if any | Depending on Customer needs
9 |  | Location masters – Here you can attach the users and the location rights.
10 |  | Bank Master.
11 |  | Accounts Master with Accounts Category
12 |  | Multi Currency enablement and set the exchange rates
13 |  | Customer Master 1. Customer ID* 2. Customer Name* 3. GSTN Number and state 4. eMail id 5. Address
14 |  | Supplier / vendor master 1. Supplier ID* 2. Supplier Name* 3. GSTN Number and state 4. eMail id 5. Address
15 |  | Product master upload 1. Product ID less than 20 char* 2. Description less than 250 char* 3. Unit of measurements* 4. Do you keep stock / Inventory = Yes * 5. Product Group 6. If the QTY is entered then Unit Price is important as it gives inventory valuations. * 7. Enter Selling price 8. Check Purchase or Sales TAXES (VAT/ Excise / Non Excise) 9. Check whether product is maintained in “batches” or not 10. HSN Codes
16 |  | Bill of Materials: To make a finished goods (FG), what and all raw materials (RM)/components required
17 |  | Employee Master - You can attach the Login ID to employees.
18 |  | Sales persons and their commission details
19 |  | Quality test cases templates, if any
20 |  | Customer and Product Price lists
21 |  | Supplier and product price lists
17 | Users | List of created users and their access permissions
1 | Prints | Check PO Print | Purchase Order print format
2 |  | Check Invoice Print | Print format and contents
1 | Transactions | Customer open invoices list. Enter the invoice details against each Customer with 1. Invoice number 2. Date of transactions 3. Balance amount to receive | As on Cut off date
2 |  | Customer open Bills list. Enter Supplier open Bills details against each Supplier with 1. Bills / GRN number 2. Date of transactions 3. Balance amount to Pay | As on Cut off date
3 |  | Bank details - Opening Bank and Cash details. This is done, if NO Trial balance data is entered as the opening BANK and CASH balance entries are required for the transactions | As on Cut off date.
4 |  | Opening stock details with Locations. 1. Enter RM, FG, WIP items stocks as on the cut-off date 2. Check the stocks and in UOM that’s been stored. 3. Enter the stocks against BATCH Numbers, if any 4. MUOM and other conditions, if any | As on Cut off date
5 |  | Opening trial balance. 1. Check the report format. 2. Identify the Accounts category that’s missed, if any. 3. Check the total values and DB and CR are matching | As on Cut off date
6 |  | Any customer specific needs to be addressed

## Issues List
| Date | Customer Issues | Issue Raised | Staus | Remarks | Comments
1 | 2018-01-01 | 1 Quantity value is not showing in Inventory |  | Resolved | Shown the report | eMail on 22 Mar 2018
|  | 2. TDS % Rate proper not shoving like 1%,5%, 20% |  | Open
|  | 3. Prepare a Tax Invoice as per our Billing Format in your software. |  | Open